## Slide 1: NCAP QI collaborative round two - shared learning session four
19 June 2025 2.00-4.00pm

## Slide 2: NCAP QI collaborative round two shared learning session four 19 June 2025 2.00-4.00pm
Team name: early intervention service
Team locality: cornwall

## Slide 3: Our QI original aim statement
We are the Early Intervention in Psychosis Service in Cornwall, consisting of Jordan, Hazel and Catherine who are all care coordinators in the team.
In the 2023 NCAP audit, our service scored ‘needs improving’ for their offer of carer education and support. Therefore, we applied for the QI project to help us build on this. With this in mind, our original aim was:
‘To increase the uptake of carer’s support to reach 50% of friends and family on our caseload. We aim to do this by May 2025. To achieve this, we will be promoting and facilitating a mixture of 1-1 appointments and group opportunities to meet the expectations highlighted in the data from our carer survey’.

## Slide 4
Why we care about carers
We recognise that psychosis can appear as a fog that doesn’t just affect the individual but can also seep into the lives of family and friends around them.
Studies have shown family caregivers of individuals with psychosis experience difficulties with finances, social restrictions and mental deterioration (Moudatsou et al, 2021). Another study into informal caregivers (ICs) confirmed that burnout could lead a risk of physical violence being exhibited, as well as escalation in behaviours from the caregiver onto the individual receiving care. It suggested that warning signs can include worsened emotional state (Gérain and Zech, 2021). It’s estimated that there are roughly 10.6 million unpaid carers in the UK (Carers UK, 2022). Another study showed that carers of people with psychosis experienced financial burden due to the time needed to provide care, requiring them to take time off work. Other common themes included a lack of social support, family conflict and poor medication compliance from the patient (Bai et al, 2020).
Clinical guidelines highlight that we can improve services by assisting service users and their carers in making informed decisions about their treatment and care. The guidelines also state we can better services by improving communication between healthcare professionals, service users and their carers.
We are aware that we see individuals for an hour out of their week, the people around them offer the support fulltime and this allows us to learn from them when it comes to providing care. This emphasises the importance building those relationships and promoting collaborative working.

## Slide 5: Our diagnostic work and conclusions
We initially started our carer programme by running groups. These groups were poorly attended, and this sparked an interest in research to see why these groups didn’t work and what could be better for offering a carer support and education programme. In our initial questionnaires it was highlighted that the majority of friends and family members would prefer a 1-1 session. Therefore, for the first part of this project was offering 1-1 carer appointments.
Barriers to attending group sessions included:
“Don’t work well in groups”
“Work commitments”
“Family, commitments”
“Concerned that I will know the people who attend in another capacity”
“Transport”
“Lack of time.”
Chart: 
| Group | 1 to 1 | Both
Data | 3 | 9 | 1
Notes: Feedback stated that people wouldn’t feel comfortable discussing personal details in a group of people.

## Slide 6
Diagnostic work and conclusions continued
Our questionnaire also highlighted that face to face was widely preferred as a method for appointments. We are
aware that it’s important to allow friends and family to have their own space to complete these sessions without the
individuals present. Therefore, we have been offering these sessions in local resource centres and have found that this
has worked really well. However, we are able to be flexible in the offering of these sessions and on 2 occasions have
offered these in people’s homes when the individual was out working. Where possible we offer both appointments in the
same place on the day to reduce staff travel time and work more efficiently.

## Slide 7
Diagnostic work and conclusions continued
For the 2024 NCAP audit, our service scored 63%, meeting criteria for ‘Performing Well’ for the carer support and education program. This means that we met our original aim for the QI project. However, we are now working towards maintaining that and improving further by continuing the work we have been doing.

## Slide 8: Overview of two of our PDSA cycles
PLAN- We conducted research questionnaires that concluded the majority of friends and family would prefer 1-1 appointments. We then discussed how we would do this and decided on days and times that worked best.
DO- We started offering and carrying out 1-1 carer appointments. We have protected time for the project on a Monday, therefore we offer the appointments on this day.
STUDY- We noticed that the uptake was a lot higher than when we were offering groups. However, on occasion we noticed that there were DNAs for the morning appointments. To combat this, we decided to send out reminders in the morning and also make 2 appointments in the day to cover a possible DNA.
ACT- Since sending out text reminders we have not had any DNAs. We are also able to work through the list of appointments more efficiently by offering 2 appointments in a day.

## Slide 9
PLAN: Following on from the last PDSA model, we noticed that we had DNAs from initial 1-1 sessions (50%). We spent
a lot of our time making phone calls, booking rooms and organising sessions and so 50% DNA rate which was not an
efficient way of working. From this it prompted us to make a change.
DO: After calling the people who did not attend their appointment, it became apparent they didn’t attend due to the
appointment being made a couple of weeks in advance and the individual forgetting. Therefore, we decided to send out
a text message reminder to the person prior to the appointment.
STUDY: Since implementing text message reminders, we have had 1 DNA out of 15 appointments. However, it was then
found out that this person’s family member was in crisis at this time and attending the appointment was not the priority
for them.
ACT: From the information we have it has been shown that sending text reminders is working well and our DNAs have
reduced significantly. Therefore, we will continue to do this going forward when delivering 1-1 sessions.

## Slide 10: Qualitative feedback
“It’s been good to ask questions without the (individual) around”.
“Definitely more useful than I thought it would be”.
"I found the 1-1 appointment helpful; it was good to have time and a place to be able to talk through what it has been like supporting my son. I found being able to ask questions away from him helpful, getting some clarification on medication helped my understanding. Which helped me discuss this with my son. I would say that I would have found having this appointment at the beginning of our involvement with the team better but still useful."
"My Sister has lots of support from various services and although I have spoken with her care co in EIT, it was good to meet with you for an appointment. I made me aware that I could phone in with any questions and a better idea what the service offer. It was good to have a chance to talk all we had been through while supporting my sister. It has highlighted how much support I offer and should try and take time for me too."
"Our son has not involved us in his care; we understood this appointment could not give us his information. However it was helpful for us to talk to you about our experiences, we asked questions about psychosis, getting general information about this helped us understand things a bit better. It was good to know how to talk to our son when unwell, you gave us some useful tips. It has been hard supporting him and knowing that others are going through something like this has provided us with some comfort"
Notes: Demonstrating sustained improvement

## Slide 11
Reflections on the experience of being part of a national QI project/impact summary
We have all enjoyed being a part of a project that allows us to be curious and gives the time to try and change things in
a flexible way, being creative. As well as that, it’s adaptable as we are able to change things to suit different people’s
needs and promoting inclusivity, being led by carer’s needs and input.
Being able to access protected time and dedicating our Mondays to work specifically on the carer education and support
programme has enabled us to offer consistent 1-1 appointments and complete the admin that comes alongside the
project. Pressures of the service still exist, but managing expectations in the wider team by ensuring our manager has
protected this time for us has been important.
The QI project has provided us with the skills and information necessary to carry this on further and continue to work and
develop on the carer support and education programme. We will do this by continuing to work using the PDSA model and
knowing that it’s okay to stop and change things if they aren’t working.

## Slide 12
Reflections cont. and next steps…
From our 1-1 sessions, we noticed that family and friends enjoy using this time as an opportunity to ask questions and
Gain validation in the way they are caring for their loved one, or getting support and advice on different situations. This
Has meant that no two sessions have been the same, and we’ve been able to build a good rapport with the people we’ve
Met.
From this, we decided that trying to incorporate a more formalised delivery of education may not work for the initial 1-1
sessions. Therefore, we have decided to keep these sessions informal as they currently are, but we have identified key
themes that people wanted more information on and created a series of educational powerpoints. These will be uploaded
to a new section of our website that we are developing to create a digital space for carers to get information and support
online.
Key themes include:
How to talk to someone with psychosis
Understanding medication
Self-care
Sleep
Drugs and psychosis
We also noticed from our sessions that friends and family
Highlighted that they wish they knew how to contact the team
In case of an emergency or for any support.
From this information we have now created a letter to be sent
Directly to identified carers/next of kin when their loved on is
Confirmed. This letter highlights our confidentiality policy, but
Also explains that we can listen to others and gives the contact
Numbers for our teams and the crisis line.
Notes: Talk about the digitalisation, redoing the carer packs and sending out links to the website when it’s up and running. Monitoring response to the educational presentations and possibly in the future running a week by week delivery of these with carers. Looking into peer support between carers, possible group chat? Linking in with local and national carer support such as POPS. The letter offering an opt out from 1-1 sessions so we’re not chasing people that don’t want an appointment.

## Slide 13: NCAP QI collaborative round two shared learning session four 19 June 2025 2.00-4.00pm
Team name: Navigo’s EIP
Team locality: North East Lincolnshire

## Slide 14: 1. Our QI team and original aim statement: To increase the uptake of Family Intervention
Notes: So, the overall project aim is to increase the uptake of Family Intervention as it had been neglected for some time due to covid issues and staffing changes.
In an attempt to move forward, four clinical members of staff embarked on the King’s college training programme for CBT FI – which is a yearlong post graduate course that came to an end in January 2025.
Initially, the aim had been to increase uptake by of FI to 25% - from the previous figure of 0 uptake. As a team, we wanted to set an achievable goal but did not anticipate the level of success we have had.

## Slide 15: 2.
Updated Run chart(s)
Chart: April 2024
| Accepted | Declined
 | 13 | 50
Chart: June 2025
| Accepted | Declined
 | 19 | 46
Notes: April 2024: -63x in total on the teams caseload – with 50x (79%) declining FI – 13x (21%) accepted and undergoing
Over a year later
June 2025-63x in total on the teams caseload – 43x (68%) declining FI – 20x (32%) currently undergoing, completed FI or are on the waiting list.
It is important to note that the data is not fully accurate given how fluid the figures are – taking into consideration that people are being discharged, pending discharge, starting a new care spells, have been placed on extended assessments etc. And so it is ever changing.
This data is based on the amount of people accepting family work and are on the waiting list, however, the final outcomes measures will be based on engagement and having at least one sessions of family work.

## Slide 16
Notes: notes: Well this has been an interesting journey, which we did not expect to be as successful as it actually is. We have found that by simply considering our approach to FI, we have completely restructured this particular intervention and how it is delivered. What made this a more simple journey and appears to be the biggest conflict for other teams, is that the team culture of acknowledging FI as a valuable resource already existed. It was written into our job descriptions and was highlighted from the start of appointment that there was an expectation to train in and deliver FI and so it came as no surprise when talks around FI implementation arose.
FI is extremely successful in achieving more positive outcomes for our service users and this was evidenced in all of the cases that the team have completed so far.
We initiated changes though team meetings, which led the team to consider the importance of language and how the interventions name itself can carry negative connotations for our service users and their family’s. To mitigate this, we constructed a new information leaflet and renamed the intervention ‘bridging the gap’.
We set aside protected time to discuss and consider potential cases that would be suitable for FI and developed protected supervision time for clinicians to seek guidance and offer a place for reflection.
We continued to utilise tactics implemented for uni work – such as using Dictaphones to record sessions and listened back on these session to reflect on any challenges or to formulate future direction – this is something that helped the team enormously.

## Slide 17: 4. Case overview:
Notes: Family intervention should be considered as important as all other forms of intervention within EIP. Navigo EIP acknowledge it as part of the job role and it is an expectation that all practitioners train at some point.
At present, we have four practitioners trained in CBT FI and four trained in BFT FI, which provides a nice balance.
We are able to cherry pick cases and consider during supervision sessions, which model would be most applicable for each family in order for them to get the best out of the intervention. We have even started to amalgamate the models to fit, which is proven to be more beneficial to families particularly where there is neurodiversity.
Having just completed my own training (in CBT FI), I was fortunate enough to have completed work with one family and have the opportunity to watch them grow and develop.
The family consists of Mum and Daughter, both of whom moved from Romania when daughter was around 12 years old. Mum then married Step-Dad.
Daughter, who is the service user, presents with fluctuating psychosis due to complex trauma and substance abuse. She has been under the care of the team for four years - and has struggled to engage throughout. She has been offered a great number of interventions but has never been able to commit.
She chose not to engage in the FI, so initially I did feel apprehensive as to how successful this could actually be.
Myself and a colleague spent a year working with Mum and Step-Dad and the main focus of FI was applied to communication skills and the construction and recognition for personal boundaries.
This was really important as Mum, as the main source of support for Daughter, had her own mental health diagnosis of EUPD and so struggled to regulate her own emotions and responses. This meant that prior to the intervention, all interactions between Mum and Daughter would result in heated arguments and conflict.
However, as the sessions progressed, Mum was able to recognise her own limitations and set boundaries to protect her and her daughter’s mental health. She was able to reflect and consider alternative responses to her daughter and was taught to explore consequence.
The sessions also allowed us to identify Step-Dad’s skills and ability to see situations from both Mum and Daughter’s perspectives, taking note of the impact that Daughter’s psychosis would take her line of thinking.
Through this being promoted, he was able to support his wife to remain more level headed and continue to explore her own communication styles and responses once the sessions had been completed.
The outcome if this saw an overall change in the dynamics of the family through less hostility, less stress and an increase in Daughter’s ability to engage with the service - something that had not been anticipated in the initial stages.

## Slide 18
Notes: So this slide is a clip from the Mum herself and her experiences of the Family Intervention.

## Slide 19
From isolation to inclusion; why engaging families changes everything in psychosis care & recovery
Notes: All the literature available paints FI in a very positive light and highlights that the intervention only ever has positive outcomes for the services users and their families.
Through psychoeducation, families are provided with the opportunity to understand the specifics of psychosis and explore how this guides the thoughts and actions of their loved ones.
It allows for a more joined-up approach in the construction of care planning and enables the family members to feel a level of support and develop a sense of security – which can be instrumental in reducing stress, this being a key objective of FI.
As an example of this, the case study, prior to engaging in the FI, Mum would constantly make contact with most members of the team extremely distressed and requiring a considerable amount of time to support and help her to regulate. It got to a point that she was dominating the service, which was leading to signs of burnout in staff – a situation that I am sure everyone here today can relate to.
In the initial stages of the FI, Mum would present with high expressed emotion and also relayed a narrative that indicated her caring role was burdensome due to the fact that her Daughter was unable to recognise her own and her Mum’s needs. And as previously stated, this led to frequent breakdowns in their relationship and encouraged the daughter to further isolate herself. The main direction of the FI focused on communication styles, exploring typical experiences for someone with psychosis and recognising personal limitations.
As the sessions progressed, we observed Mum begin to reflect on her own responses to her Daughter and conclude that this needs to be a consideration moving. She started to view her daughter with more warmth and we saw the hostility and defensiveness in her character reduce. Mum started to see her Daughter in a more positive regard, presenting less critical narratives and showing more of understanding towards her and her mental health experiences.
This had a really positive outcome for Daughter, who actually started to engage in the support being offered to her and we started to see a change in her attitude towards services.

## Slide 21: NCAP QI collaborative round two shared learning session four 19 June 2025 2.00-4.00pm
Team name: PATH
Team locality: Hertfordshire

## Slide 22: 1. Our QI team and original aim statement
Our QI team:
Wide mix of the team, including Family Intervention leads, operational and psychology leads, expert by experience and FI therapists.
Project Aim and Progress:
Initial Goal: The project aimed to increase family intervention (FI) uptake within the PATH service from 8% to 16%.
Current Status: Despite not achieving the target, the team has made significant progress in understanding the challenges, diagnosing the mechanics of what needs to change and implementing change ideas.
Challenges: Resource limitations – both staffing numbers & length of time to deliver therapy and number of sessions: neurodiversity and reasonable adjustments. Staff confidence of staff delivering & offering FI, culture within service and admin tasks.

## Slide 23: 2. Our diagnostic work and conclusions
Resource limitations:
  Impact on Uptake: The project faced challenges due to limited resources, which affected the ability to increase FI uptake.
  Staffing Issues: There was a need for more dedicated staff to support FI delivery, to enable non- qualified staff to be part of delivering FI with a qualified therapist, supervision, training, visibility in MDTs, clinical discussions, caseload reviews
  Length of therapy/no. of sessions related to: neurodiversity, learning disability, physical health and reasonable adjustments required
Admin Tasks:
  Onboarding service users into FI, arranging time that works for everyone, do they still want therapy after being on waiting list for so long?
  Administrator Contact: Efforts to have an administrator contact service users were time-intensive and faced issues with matching availability.
Culture:
Moving from specific roles completing FI to making it everyone’s business – greater presence of staff & it’s on the agenda within all clinical meetings
Training:
  Training Adjustments: Training sessions were restructured to improve staff confidence and reduce dropout rates. This included better communication about course expectations and support.
  Role Play Training: Simulation training sessions helped improve staff confidence. Initially, staff were hesitant, but feedback indicated positive experiences once they participated.
  Peer Supervision: Improving on existing peer supervision sessions allowed staff to reflect on their practice and improve their skills. We have also re-established a peer supervision for FI supervisors.

## Slide 24: 3. Measures
SPIKE ( internal electronic data dashboard): Recording of offer of and take up of therapy
Fortnightly tracking meetings:
to review allocated cases,
to look at pairings,
narrative attached to any delays or extension of treatment,
pausing of therapy and non engagers –
NICE guidance: Minimum of 10 sessions, we’ve identified we work to 15 sessions
Reviewing time on FEP pathway & time on FI waiting list

## Slide 25: 4. Overview of two of our PDSA cycles
Resource:
  Administrator Contact: Efforts to have an administrator contact service users were time-intensive and faced issues with matching availability. Discontinued but adapted to checking in with service user if they still want to proceed with FI before allocation to therapists. It has also helped to put together a “not able to make contact process for taking off the waiting list.
Staff Confidence and Engagement:
  Training Adjustments: Training sessions were restructured to improve staff confidence and reduce dropout rates. This included better communication about course expectations and support.
  Role Play Training: Simulation training sessions helped improve staff confidence. Initially, staff were hesitant, but feedback indicated positive experiences once they participated.
  Peer Supervision: Improvement of peer supervision sessions by increasing the number of groups in place to allow us to reduce numbers of staff in each group to allow more time for case discussions and allowed staff to reflect on their practice and improve their skills. We have also reestablished a peer supervision space for FI supervisors.

## Slide 26
5. Change ideas = Business as usual
FI leads are now contacting service users & families, rather than pairings making contact in lieu of the administrator doing this previously.
The “not able to make contact” process to manage service users on the waiting list.
Fortnightly allocations review meeting – is a more thorough review of all “active” FI cases & waiting lists
Training and Role-Play Sessions in simulation hub: Positive feedback; ongoing use to build staff confidence
  Clearer communication around training staff to be a qualified FI therapist, expectations and support leading to less drop out rates
Our 4 weekly QI planning meetings will become a steering group – to continue to have the dedicated time and space to continue to test out change ideas
Learning from Other Teams: Adapted ideas like changing terminology and using leaflets; considering extending supervision sessions

## Slide 27: 5. Positive outcomes:
Increased Visibility and promotion of Family Intervention:
  Dedicated FI Therapists: The appointment of dedicated FI therapists has improved visibility and support within the service.
  Representation in MDTs: FI therapists now have a presence in Multi-Disciplinary Team (MDT) meetings, enhancing visibility and support for FI, enabling clinical discussions focusing on evidenced based outcomes ( NICE)
Cultural Change:
  Understanding and Acceptance: Efforts to change the culture within the trust have led to better understanding and acceptance of FI as a valuable intervention.
  Staff Engagement: Increased engagement from staff at all levels to deliver FI, including senior management, has helped promote FI and increase delivery.
Peer Support:
  Supervision Sessions: The improvement of peer supervision sessions by introducing a 3rd group has allowed us to reduce our number of staff in each group, this has helped staff improve their practice and confidence. We have reestablished a peer supervision space for FI supervisors also.
Notes: Demonstrating sustained improvement

## Slide 28
6. Next steps:
Continued Training:
  Train the Trainer: Plans to train more staff, including support workers, through a "Train the Trainer" program to increase capacity for delivering FI.
  Wider Training: Training staff outside of the existing groups to build capacity and support for FI delivery.
Ongoing Review:
  Steering Group/PDSA Sessions: The importance of continuing PDSA sessions to review progress and maintain momentum is fundamental in continuous improvement. These sessions will help ensure that the on-going project remains high-profile and focused.
Resource Allocation:
  Dedicated FI Leads: The appointment of dedicated FI leads across the service will help improve oversight and increase the number of cases that can be in therapy at any one time.
  Visibility in MDTs: Increased visibility of FI therapists in MDT meetings will help promote FI and support its delivery.
  Learning from Other Teams: Adapted ideas like changing terminology and using leaflets; considering extending supervision sessions

## Slide 29
6. Reflections on the experience of being part of a national QI project/impact summary
At the beginning of the project it felt like we were “battling with enormous complexities, size of service and geographical area, trying to turn a massive ship around”
Achievements: Identified problems, implemented change ideas, completed PDSA cycles, adapted change ideas to become business as usual and appointed dedicated therapist lead
Cultural Change: Improved staff & organisational understanding and engagement, making family intervention everyone’s business, adapted practices from other teams
Future Outlook: Progressing towards a more robust infrastructure, positive changes already seen with an increase in dedicated FI leads across the service and bring all staff into the conversation. Continued focus on improvement with monthly PDSA sessions
Reflections from Expert by Experience: Tim Dobson

## Slide 30: NCAP QI collaborative round two shared learning session 13th February 2025
Team name: Early intervention team in psychosis
Team locality: Warrington & Halton

## Slide 31: 1. QI team membership
Team members:
Stephanie Smith, Clinical Team Manger.
Tracy Harrison, Clinical Lead.
Rachel Nolan, Research Assistant.
How are you involving people with lived experience in your QI work ?
Those that have been through the process of BFT are assisting the service with re-design of the leaflets, to help make the offer more appealing and hold greater meaning.
Carers, who have participated in Behavioural Family Therapy, to provide video/ audio recordings.
Notes: Prompts- please list your QI team membership including lived experience representatives (don’t have not provide names if they do not consent)

## Slide 32: 2. What’s your problem area for improvement?
FI is needed to reduce relapse.
Data informed us that: not enough meaningful offers are being made.
Team is not delivering enough FI to patients & families.
Data not captured correctly due to codes used on Rio.
Staff’s enthusiasm towards FI.
Notes: Prompts- what is the problem you are tackling ? E.g. improve our team's performance on the Fi standard- can add details about how and why you chose to focus on this standard.

## Slide 33: 3. What diagnostic tools/exercises did you use to better understand your problem?
Barriers
Themes: Time, Caseloads, Confidence, Engagement, Education.
“Completing the training a while ago, therefore not feeling comfortable with facilitating”
“Managing a big caseload and not working full time hours.”
“Not interested, don't feel it is relevant to their care”
“Complex relationships with family, engagement and motivation can be poor”
Change ideas
Themes: Staffing, Supervision, Training, Update materials
“Protected time for staff to deliver FI, Regular supervision. Newly trained doing FI with experienced staff. Top up training”
“Increase in number of care coordinators to free up time for staff to engage in BFT work with families”.
“Think leaflet for family members could have more about the research into BFT, and degree of success for people that engage with it”.
“I do feel that our team having a full time staff member to focus on FI would benefit us”.
Notes: Prompt- what have done to better understand your problem ? Staff surveys’, team meetings, collected your baseline data (add in what this is)
Staff Survey:
Importance of FI: Scores range from 4-10 (average 9) FI apart of your role: Scores range from 1-10 (average 6) Confidence in explaining to families: 3-10 (average 8) Confidence in delivering to families: 4-10 (average 7)

## Slide 34: 4. What was your key learning about the area you want to improve?
Time/ non protected time
Workload/ high caseloads
Confidence
Team not viewing FI as a part of their role
Education to patients & families
Feeling the family are to ‘blame’
Not interested/ feeling it is not important
This Photo by Unknown Author is licensed under CC BY
Notes: Prompt- did anything come up you didn’t expect ? It would be helpful for teams to think about whether there was any difference between what you thought was the problem versus what actually came up via survey's, conversations with staff/service users, trends in baseline data etc.

## Slide 35: 5. Statement To increase the uptake of BFT, for all eligible patients and their families. The aim is to have a 10% increase in the uptake by May 2025.
Notes: Prompt- E.g to Improve the uptake of Fi for all eligible service users by 10% by May 2025. please add in some detail about how your team arrived/agreed on your aim statement.

## Slide 36: 6. What are you going to measure?
Regular supervision
Offering BFT earlier
Updating the BFT leaflet, provided to patients and families
Expert by experience to discuss with families on their experience of BFT.
Regular training/ refresher role plays.
Attendance sheet, feedback sheets.
Monitoring offers made in MDTs.
Survey to staff and patients/ families on their views of the current leaflet.
Uptake numbers of BFT from families.
Confidence scale, pre & post EIT away day.
Change ideas
Measure
Notes: Prompt- thinking about your aim and change ideas what are you going to measure to understand the impact of your change ideas ? E.g. ongoing outcome measure will be how many families start FI per week/month or staff confidence levels before and after refresher training etc.

## Slide 37: 7. Next steps
1) Supervision: To ask facilitators to add role plays to supervision.
There has been a request that BFT supervisions incorporate opportunity for role play.
2) Offer BFT earlier: To discuss in MDT’s, organise carers group (once a month) for new patients on the First Episode Psychosis (FEP) pathway.
This is now ongoing within the EIP weekly MDT. This has also been moved to the first agenda of the MDT as it was noted that this may allow emphasis to the importance of its delivery.
3) Leaflet: Distribute survey to staff and patients/ families.
This has been actioned, there was not an initial great response from staff, so a further push has been made to gain further data.
4) Expert by experience: Ask families to provide video/ audio videos.
1 family to date has been approached.
5) Training/ role plays: Organise EIT Away Day.
During the recent away day on the 15th October, simulations were run for staff to gain an experience and exposure to the delivery of BFT. Staff were provided with opportunity to observe the delivery of a particular skill (example- problem solving).
Notes: Prompt- this can include a list of the change ideas you have come up with (can be provisional ones and don’t have to be in the order you are going to test them in if that’s not been decided), reviewing your survey results, meeting with carers groups etc.

## Slide 38: 8. So how are things looking?
Early Intervention - Number of service users with an open FEP pathway with activity of ‘EIP – Family intervention for psychosis’ |  | 30.0% |  | 10.8% | 9.5% | 10.0% | 9.9% | 9.7% | 9.2% | 9.4% | 9.5% | 10.5% | 11.9%
April May June July Aug Sept Oct Nov Dec Jan
Notes: Prompt- did anything come up you didn’t expect ? It would be helpful for teams to think about whether there was any difference between what you thought was the problem versus what actually came up via survey's, conversations with staff/service users, trends in baseline data etc.

## Slide 39: 9. How are we keeping track?
Notes: Prompts- please list your QI team membership including lived experience representatives (don’t have not provide names if they do not consent)

## Slide 40: 10. What’s next? Expert by experience- gaining feedback from those currently engaging in BFT and identifying those that may wish to assist with promotion of BFT to others. Will be invited to participate in next scheduled carers group that is delivered by EIP. Due Feb 2025.
Notes: Prompt- E.g to Improve the uptake of Fi for all eligible service users by 10% by May 2025. please add in some detail about how your team arrived/agreed on your aim statement.

## Slide 41: NCAP QI collaborative round two shared learning session four 19th June 2025 2:00-4:00PM
Team name: Early intervention in Psychosis team- MERSEYCARE
Team locality: Warrington & Halton

## Slide 42: 3 sides to every story?
Trust View
Patient View
Staff view

## Slide 43: Where are we now?- Trust perspective
2024 April May June July Aug Sept Oct Nov Dec 2025 Jan Feb Mar Apr May Jun
10.8% 9.5% 10.0% 9.9% 9.7% 9.2% 9.4% 9.5% 10.6% 12.3% 14.2% 13.5% 14.4% 16.4% 16.9%
This Photo by Unknown Author is licensed under CC BY-NC

## Slide 44
Danny CBTp -
‘I can now see the benefit of starting BFT sooner with patients new to the pathway, it really helps with the overall formulation’
Helen SNP- (ongoing session 7)
‘It’s good, especially when you get a good family who are really eager to get engaged’
Richard SNP- ‘I prefer to do it with my own patients, I have learned more in that one hour about my family, than I have over the past year as a key worker. Family hold the key to that locked door’
Osarogie- Student Nurse
After witnessing a BFT session, I feel that all services should be offering this!
Staff perspective

## Slide 45
Staff Perspective
Nic SNP-
‘I was working with a family and I noticed that an individual would always respond with a no when covering the making a positive request section. The receiving family member noticed this and when this was discussed, the person responded by saying that they felt they were giving them an option. Consider the use of words that are used, especially if any of the family have any additional complex needs
Lou Team Sec-
I am not BFT trained, but I do have regular communication with patients and their carers/family members as the calls come directly through to the office. I have heard a significant change first hand- plus Its cheaper and less messy than a gun!
Debbie- STR
‘It really helps improve communication skills, when we get stressed, we forget how to communicate kindly.
I tell my families, that from the training, I utilise those skills at home.
We don’t just preach, we practice! We are not teaching others what they don’t already know, we are just reminding them of those key steps to continue to be effective!
Leanne SNP-
I have just trained in BFT and I am waiting to start with my first family. The team are currently working with one of my patients and they have been able to feedback information to me that I just don’t see when I am attending my keyworker visits. With this information, it will help me navigate my future contacts.

## Slide 46: Tips- Staff perspective
This Photo by Unknown Author is licensed under CC BY-SA
‘we need to ensure that we are strict with the time- I suggest that you implement a timer to keep you on track, its helped me’- Michelle SNP
Paul SNP- (ongoing, at session 4)- ‘BFT is
Boss to be fair, its actually good,
I don’t know whether to start taking out
the family assessment to all of my patients
to help find out more about the family’.
Karina OT-
‘I understand people are anxious about BFT,
when you are in it, it will dissipate quickly,
always have your manual’.
Hayley SNP-’Invest in your patients
and they will invest in you too’
‘Richard SNP- Prepare before, it helps with the structure’
Scott SNP- (session 10)-
‘ Don’t be afraid of being flexible, especially around the family. We had a family and at the observed problem-solving section, the patients partner asked why are we doing this.
This led to an open conversation about what aspects would be beneficial and this allowed us to keep the engagement with the family. I feel if we hadn’t done this, they wouldn’t have continued’.

## Slide 47
Debbie- STR (10 sessions)-
‘you saved our marriage’ Patient Perspective
Hayley- SNP- (38 sessions)
‘It's an underrated intervention; it's probably THE most important intervention that we offer’.
I was working with a male who was aged 21 years of age who had ADHD and psychosis. The aim of this was to help improve his relationship with his mum.
He did not wish to engage initially, but as this progressed, he became more comfortable.
Michelle SNP- (18 sessions)
‘I remember thinking that I was attending a BFT sessions with parents who were professionals, an educated family, that I worried may not have been responsive. They fully embraced the process, and this helped me reflect that it isn’t about teaching others to suck eggs, the skills are transferrable outside of the family and this is the note that I take in now, to all of my BFT sessions. BFT knows no bias!’
Dawn SNP (14 sessions)
‘I was working with a family, who’s son was our patient, he also experienced autism. The implementation of BFT made considerable differences for the family. It did this by reducing the frequency of his autism meltdowns. I feel that this was achieved as it provided our patient opportunity and time to speak and his observed behaviours that family struggled with reduced. He got his voice again. The sessions were chaotically wonderful’.

## Slide 48
Did the Quality Improvement work?
To increase the uptake of BFT, for all eligible patients and their families. The aim is to have a 10% increase in the uptake.

## Slide 49
YES

## Slide 50
What's next for Warrington and
Halton EIP BFT QI?
1 Gain recordings from staff, so this can be used within carer focused education programmes as a way to encourage referrals
2 Gain video recordings from patients that have completed BFT
Liaison currently being undertaken with information governance and volunteering service within trust

## Slide 52
Please take a couple minutes to complete the feedback poll now available. Your feedback will help the NCAP team shape our future QI work!

## Slide 53: NCAP Update
Available NCAP QI drop-in coaching slots:
June
June 24th – 10:45am & 11:30am
July
July 29th – 10am, 10:45am, 11:30am, 12:15pm
July 30th – 1pm, 1:45pm, 2:30pm, 3:15pm